## Individulal Contributions
Date | Member | Activity | Contribution | Evidence | Status
24/08/2026 | Zilungile Nkambule Sphamandla Madela | Requirements | Analysed stakeholder requirements | SRS commit | Completed
28/08/2026 | Zilungile Nkambule | GitHub | Created repository structure | GitHub commit | In Progress
27/08/2026 | Tsepang Motloli Kemelo Malikoe | Feasibility | Completed technical feasibility | Report | Completed
28/08/2026 | Tsepang Motloli Kemelo Malikoe | Risk Register | Identified project risks | Risk register | Completed
24/08/2026 | Sphamandla Madela, Zilungile Nkabule | Progress Tracker | Recorded stakeholder feedback | Meeting notes | Completed
24/08/2026 | Sphamandla Madela, Zilungile Nkabule | Stakeholder | Recorded stakeholder feedback | Meeting notes | Completed

## Group Contributions
Task ID | Phase | Task | Responsible Member | Start Date | Due Date | Status | % Complete | Evidence | Notes
T01 | Planning | Identify stakeholder problem | Zilungile Nkambule Sphamandla Madela | 24/08/2026 | 25/08/2026 | Completed | 100% | Meeting notes | Stakeholder problem was investigated and the current informal IT support process was documented.
T02 | Requirements | Gather stakeholder requirements | Zilungile Nkambule Sphamandla Madela | 26/08/2026 | 28/08/2026 | Completed | 100% | Requirements | Stakeholder needs and system requirements were identified and documented.
T03 |  | Prepare SRS | Zilungile Nkambule Sphamandla Madela | 26/08/2026 | 03/09/2026 | In Progress | 70% | SRS | Requirements were consolidated and documented in the updated Software Requirements Specification (SRS).
T04 | Feasibility Study | Feasibility Report | Kemelo Malikoe Tsepang Motloli | 27/08/2026 | 01/09/2026 | Completed | 100% | Feasibility report | Technical, operational, economic, schedule, legal and ethical feasibility were assessed.
T06 | Risk Register | Create risk register | Kemelo Malikoe Tsepang Motloli | 28/08/2026 | 01/09/2026 | Completed | 100% | Risk register | Ten project risks were identified, assessed and assigned mitigation and contingency actions.
T07 | GitHub | Create repository | Zilungile Nkambule | 28/08/2026 | 02/09/2026 | In Progress | 70% | GitHub | Repository/documentation structure was prepared to support project collaboration and evidence of participation.
T08 |  | Upload documentation
T09 | Project Management | Update Microsoft Project Plan | Sive Lwana Kwanda Gosa | 24/08/2026 | 02/08/2026 | Completed | 100% | MS Project | Project activities, responsibilities and progress were documented for Phase 1.
|  | Progress tracker | Karabo Smous Tshapo Moloi | 28/08/2026 | 02/09/2026 | Completed | 100% | Project Tracker
T10 | Development | Flutter mobile application |  |  |  | Not Started | 0%
T11 |  | ASP.NET Core application |  |  |  | Not Started | 0%
T12 |  | Supabase database |  |  |  | Not Started | 0%
T13 | Integration | Integrate applications |  |  |  | Not Started | 0%
T14 | Testing | System testing |  |  |  | Not Started | 0%
T15 | Presentation | Prepare presentation |  |  |  | Not Started | 0%

## Stakeholder Engagement
Date | Stakeholder | Engagement Type | Purpose | Key Feedback | Decision/Action | Responsible | Evidence
26/08/2026 | IT Support | Meeting | Understand current process | Issues reported informally | Develop central ticket system |  | Meeting notes
28/08/2026 | IT Support | Requirements confirmation | Confirm ticket fields | Ticket requires category, urgency and description | Add fields to SRS |  | Confirmation
28/08/2026 | IT Support | Feedback | Confirm dashboard needs | Technicians need ticket filtering | Add filters |  | Meeting/WhatsApp

## Challenges And Actions
Challenge ID | Challenge | Impact | Action Taken / Planned Action | Status
C01 | Stakeholder availability for meetings and requirement confirmation was limited. | It delay confirmation of requirements. | We scheduled the meeting in advance and use written confirmation or alternative communication where necessary. | Managed
C02 | Time available for Phase 1 documentation and planning was limited. | It placed pressure on completion of planning deliverables. | We prioritised SRS, feasibility, risk, stakeholder evidence and project-tracking activities before Phase 2 development. | Managed
C03 | Access to real departmental data and infrastructure was limited. | Development and testing cannot rely on confidential departmental data. | Used representative sample/test data and exclude confidential stakeholder information from GitHub and demonstrations. | Managed