## Group Contributions
Task ID | Phase | Task | Responsible Member | Start Date | Due Date | Status | % Complete | Evidence | Notes
T01 | Planning | Identify stakeholder problem | Zilungile Nkambule Sphamandla Madela | 20/08/2026 | 28/08/2026 | Completed | 100% | Meeting notes
T02 | Requirements | Gather stakeholder requirements | Zilungile Nkambule Sphamandla Madela | 20/08/2026 | 28/08/2026 | Completed | 100% | Requirements
T03 |  | Prepare SRS | Zilungile Nkambule Sphamandla Madela | 20/08/2026 |  | Completed | 80% | SRS
T04 | Feasibility | Technical feasibility | Kemelo Malikoe Tsepang Motloi | 20/08/2026 | 24/08/2026 | Completed | 100% | Feasibility report
T05 |  | Operational feasibility |  | 20/08/2026 | /08/2026 | Completed | 100% | Feasibility report
T06 | Risk | Create risk register | Kemelo Malikoe | 20/08/2026 | /08/2026 | Completed | 100% | Risk register
T07 | GitHub | Create repository | Zilingile Nkambule | 20/08/2026 | /08/2026 | Completed | 100% | GitHub
T08 |  | Upload documentation |  | 20/08/2026 | /08/2026 | In Progress | 70% | GitHub
T09 | Project Mgmt | Update Microsoft Project | Sive Lwana; Kwanda Gosa | 20/08/2026 | /08/2026 | In Progress |  | MS Project
T10 | Development | Flutter mobile application |  |  |  | Not Started | 0%
T11 |  | ASP.NET Core application |  |  |  | Not Started | 0%
T12 |  | Supabase database |  |  |  | Not Started | 0%
T13 | Integration | Integrate applications |  |  |  | Not Started | 0%
T14 | Testing | System testing |  |  |  | Not Started | 0%
T15 | Presentation | Prepare presentation |  |  |  | Not Started | 0%

## Individulal Contributions
Date | Member | Activity | Contribution | Evidence | Status
28/08/2026 | Zilungile Nkambule Sphamandla Madela | Requirements | Analysed stakeholder requirements | SRS commit | Completed
28/08/2026 | Zilungile Nkambule | GitHub | Created repository structure | GitHub commit | Completed
28/08/2026 | Tsepang Motloli Kemelo Malikoe | Feasibility | Completed technical feasibility | Report | Completed
28/08/2026 | Tsepang Motloli Kemelo Malikoe | Risk | Identified project risks | Risk register | Completed
24/08/2026 | All | Stakeholder | Recorded stakeholder feedback | Meeting notes | Completed

## Stakeholder Engagement
Date | Stakeholder | Engagement Type | Purpose | Key Feedback | Decision/Action | Responsible | Evidence
| IT Support | Meeting | Understand current process | Issues reported informally | Develop central ticket system |  | Meeting notes
| IT Support | Requirements confirmation | Confirm ticket fields | Ticket requires category, urgency and description | Add fields to SRS |  | Confirmation
| IT Support | Feedback | Confirm dashboard needs | Technicians need ticket filtering | Add filters |  | Meeting/WhatsApp